**MOS 4999E-Undergraduate Honors Thesis Timeline for Completion**

**Major goals to be completed by October 31st:**

* Identify Research question and hypotheses
* Identify relevant variables and measures
* Continue background reading for literature review

**Major goals to be completed by November 30th:**

* Complete and submit ethics protocol
* Complete and submit request to access participant pool
* Receive training from supervisors on how to create online surveys
* Set up Qualtrics account
* Continue background reading for literature review

**Major goals to be completed by December 31st:**

* Sort notes on background reading
* Begin writing introduction and literature review
* Create online surveys

**Major goals to be completed by January 31st:**

* Complete writing of introduction and literature review
* Organize dates for running in-lab part of the study
* Post study on Sona for students to sign up for
* Begin collecting data –post first online survey and run labs

**Major goals to be completed by February 28th:**

* Complete data collection
* Write Method section
* Analyze data with supervisors

**Major Goals to be completed by March 31st:**

* Write up results and discussion sections
* Submit first draft to supervisors
* Incorporate feedback from supervisors into a second draft
* Submit second draft

**Major Goals to be completed by April 30th:**

* Incorporate feedback for supervisors into a final paper
* Submit final thesis